## Sheet1
S. No | Division No | Name of the project | AS Financial Year | Work grounded/hand over date | Type of work (Layots/Roads/parks/lakes/O&M/Heritage/others) | Name of the work | AS file No | AS to MC or Govt | AS Details (GO No./Note file No, Dept & Amount) (Rs. in Crs) | AS date | Revised AS details (if any) | TS Part (A+B) Details, RTS Details (if any) | Estimate amount (Rs. in Crs) | Tender Notice details (No & date) | ECV (Rs. in Crs) | Period of completion | Tenders submission first date & last date | Evaluation details (Financial) | Quoted TCV & TP % (Rs. in Crs) | Name of the agency | Recall details if any | LOA No & Date | Notices of any cancellation (if any) | Agreement No | Agreement date | Deviations (Details, Reasons, excess/less%) | EOTs (Details, Reasons, time period) | Workslip (Details, Reasons, excess/less%, dt of approval, work done amount & total amount including all provisions ) | Status of the work | Expenditure incurred so far (including taxes) (Rs. in Crs) | Expenditure incurred so far (excluding taxes) (Rs. in Crs)
[30 empty] | - | -
| VI | Inmulnarva Layout | 2022-23 | 15.12.2022 | Layout | Providing Infrastructure facilities for the proposed layout Inmulnarva (V), R.R District |  | Govt | G.O.Ms.127 | 13.07.2022 | - | 102 | 50 | HMDA/DEV/CE/23/2022-23 dt.01.09.2022 | 55.29 | 8 Months |  |  | 55.24 Cr & (-)0.10% | M/s NCC Limited' |  | 14572/HMDA/DEV/CE/Inmulnarva &Lemoor/2022-23 dt.16.11.2022 |  | HMDA/DEV/CE/37/2022-23 | 15.12.2022 |  |  |  | Work is completed
| VI | Lemoor Layout | 2022-23 | 15.12.2022 | Layout | Providing Infrastructure facilities for the proposed layout Lemoor (V), Kandukur (M) |  | Govt | G.O.Ms.No.125 | 13.07.2022 | - |  | 52 | [15 empty] | Work in progress
| VI | Thorrur Layout | 2022-23 | 16.09.2023 | Layout | Providing Infrastructure facilitiesin Sy.No.383/1 at Thorrur (V), Abdullapurmet (M) RR Dist |  | Govt | G.O.Ms.No.6 | 21.01.2023 | - | 89 | 76 | HMDA/DEV/CE/43/01/2022-23 dt.25.03.2023 | 53.51 | 9 Months |  |  | 53.03 Cr & (-)0.90% | M/s NCC Limited' |  | 14682/HMDA/DEV/CE/Thorrur&Kurmalguda/2022-23 dt.23.07.2023 |  | HMDA/DEV/CE/20/2023-24 | 16.09.2024 |  |  |  | Work in progress
| VI | Kurmalguda Layout | 2022-23 | 16.09.2023 | Layout | Providing Infrastructure facilities in Sy.No.46/p at Kurmalguda (V), Balapur Dist |  | Govt | G.O.Ms.No.6 | 21.01.2023 | - |  | 13 | [15 empty] | Work in progress
| VI | HUDA Heights | 2024-25 |  | Layout | Providing Infrastructure Facilities for the Proposed Layout at HUDA Heights (H1 & H3) I Sy.No.102/1 of Hakimpet(V), Shaikpet(M), Hyderabad |  | Metropolitan Commissioner |  | 19.09.2024 |  | 4.5 | 4.5
| VI | HUDA Heights | 2024-25 |  | Layout | Providing Infrastructure Facilities for the Proposed Layout at HUDA Heights (H2) I Sy.No.102/1 of Hakimpet(V), Shaikpet(M), Hyderabad |  | Metropolitan Commissioner |  | 19.09.2024 |  | 9.3 | 9.3
| VI | HUDA Heights | 2024-25 |  | Layout | Construction of Storm water Drain in H1 block for the Proposed Layout at HUDA Heights in Sy.No.102/1 of Hakimpet(V), Shaikpet(M), Hyderabad- |  | Metropolitan Commissioner |  | 19.09.2024 |  | 2.7 | 2.7
| VI | Bhongir Bund | 2023-24 | 04.10.2023 | Park/Bund | Strengthening and Beautification of Tank Bund at Bhongir, Telangana. |  | Metropolitan Commissioner |  | 12.06.2023 |  | 7 | 7
| VI | Pochampally Lake | 2024-25 | 29.03.2024 | Park/Bund | Developmemt of Pedda Cheruvu Lake of Pochampally Muncipality as Mini Tank Bund with Greenary and other amenities |  | Metropolitan Commissioner |  | 27.07.2024 |  | 9.7 | 9.7
| VI | Bommalaramaram | 2022-23 | 18.02.2025 | Road | Providing BT Roads, CC Roads, Street Lights and Greenary, Beautification in Bommalaramaram, Yadadri, Bhuvanagiri District |  | Govt | G.O.Ms.No.157 | 26.08.2022 |  | 20 | 20
| VI | Sangareddy | 2024-25 | 27.05.2025 | Road | Widening and strengthening the NH65 to Sangareddy - Nanded akola road NH616 via saibaba temple in Sangareddy town limits from 0/02/626 including Construction of Central media and Flood lighting in the Municiapl limits of Sangareddy |  | Govt | G.O.Rt.No.427 | 20.09.2024 |  | 12 | 12
| VI | Sangareddy | 2024-25 |  | Road | Construction of BT Road from NH 65 to Bhoolaxmamma via Kalivemula of Kandi(M), Sangareddy Dist. |  | Govt | G.O.Rt.No.427 | 20.09.2024 |  | 4.5 | 4.5
| VI | Ibrahimpatnam | 2023-24 |  | Road | Construction of ByPass Road to Ibrahimpatnam Town from Naganpally Road to Nagajuna Sagar Road @ Ibrahimpatnam Muncipality, Ranga Reddy District |  | Metropolitan Commissioner |  | 14.09.2023
| I | Neopolis Layout | 2019-20 | 23.01.2021 | Layout | Integrated Development of Kokapet Layout including Construction of Trumpet and Interchange at Narsingi (V) of Ranga Reddy District) |  | Govt | a) G.O. Ms.No. 304 MA&UD (Plg.I(1)) Dept., dt.12.12.2019- Rs. 268.00 Cr. b) GO. Ms.No. 160 MA&UD(Plg.I(1)) Dept., dt. 03.10.2020 - Rs. 80.00 Cr. | 2019-12-12 | a) G.O. Ms.No. 714 MA&UD (Plg.I(1)) Dept., dt. 10.03.2022 - Rs. 104.00 Cr b) G.O. Rt.No. 268 MA&UD (Plg.I(1)) Dept., dt. 06.05.2023 - Rs. 79.00 Cr | 531 | 531 |  |  | 18 months |  |  |  | M/s.NCC Limited |  |  |  | HMDA/DEV/CE/21/2020-21 | 23.01.2021 |  |  |  | Work in Progress | 483.05 | 393.18
|  | Providing UGD Line at Financial District Nanakramguda (V) Serilingampally (M) RR Dist | 2022-23 | 25.01.2023 | UGD | Providing UGD Line at Financial District Nanakramguda (V) Serilingampally (M) RR Dist. | 71913/HMDA/DEV/Div-I/Providing UGD at financial Dist/2022-23 | MC | 71913/HMDA/DEV/Div-I/Providing UGD at financial Dist/2022-23 | 19.10.2022 | _ | 9.04 | 9.04 |  | 6,36,96,137.00 | 9 months |  |  | 4.07 Cr(-) 26.10 % | M/s.Krushi Infras India Private Limited |  | 14602/HMDA/DEV/CE/UGD Financial/22-23 Dt: 20.12.2022 |  | HMDA/DEV/CE/48/2022-23 | 25.01.2023 |  |  |  | Work in Progress | 3.04 | 2.58
|  | Park |  |  |  | Development of Eco-Park at kothwalguda
|  | Road |  |  |  | Providing Link Road from Chenamma hotel to YR Reddy (11) at Kothwalguda (V) Shamshabad (M) RR Dist.
| II | Medipally Layout | 2023-24 | 20.09.2024 | Layout | Providing infrastructure facilities for the proposal layout at Sy.No.62 at Medipally (V), Medipally(M), Medchal-Malkajgiri(D). | 14756/HMDA/DEV/CE/Infrastructure/2023-24 | Govt. | G.O. Ms.No.160 | 14.08.2023 | _ | _ | Rs.28.00 |  | 14,02,20,832.00 | 09 Months |  |  | 13,87,06,447.01 | M/s RN Constructions |  | 14794/HMDA/DEV/CE/Medipally Layout/2023-24, Dt.09.08.2024 |  | HMDA/DEV/CE/10/2024-25 | 19.09.2024 |  | 31.08.2025 |  | Work in progress | 2.95 | 2.198
| II | Prathapsingaram Layout | 2024-25 |  | Layout | Development of infrastructure works viz., road works & CD works, 30m wide radial road, Under ground drainage linesl, Water supply lines, storm water drain, ELSR, Under ground electrical supply system and Substation in the ayout of Prathap Singarm Villege of Ghatkesar (M), Medchal-Malkajgiiri(Dist.). |  | Govt. | G.O. Ms.No.05 | 07.01.2025 |  |  | Rs.120.00
| II | Bahadurpally Layout | 2023-24 | 28.07.2023(As per LOA) | Layout | Development of Layout at Bahadurpally | 14568/HMDA/DEV/CE/Layouts/2022-23 | Govt. | G.O.Ms.No.6, MA&UD(Plg.I(1)) Dept. | 21.01.2023 |  | 13.5 | 13.5 |  | 10,05,35,600 | 06 Months |  |  | Rs.9,90,27,566/- @ (-)1.5% | M/s Shivam Infratech Pvt. Ltd. |  | Lr.No.14690/HMDA/DEV/CE/Layout/Bahadurpally/2022-23, Dt.28.07.2023, |  | HMDA/DEV/CE/21/2023-24 | 29.09.2023 | Deviation-II @3.74% Excess | EOT-II 31.10.2024 |  | Work completed | 12.31 | 9.37
[6 empty] | Construction of OHT, RCC Sump cum Pump house for development of layout at Sy.No.239,240,247 & 249 of Bahadurpally(V), Dundigal-Gandimaisamma(M), Medchal-Malkajgiri(Dist.) | [12 empty] | Rs.3,77,95,575/- @ (-)10.26% | M/s Kaveri Infra Projects Pvt. Ltd. |  | Lr.No.15100/HMDA/DEV/CE/OHT/RS&PR/BDPLY/2024-25, Dt.30.05.2025
| II | M-G Road work | 2023-24 | 12.06.2024 | Road work | Widening and strengthening of Existing Road from Miyapur “ X “ Roads on NH-65 to Gandimaisamma “X” Roads on SH Way for a total stretch of 14.00km in Medchal-Malkajgiri District. | 17/HMDA/DEV/Div-V/2021-22 | Govt. | G.O. Ms.No.195 G.O.Ms.No.48 | 29.10.2023, 13.03.2024 | _ | Rs.135.00 | Rs.135.00 |  | 104,98,13,371.00 | 12 Months |  |  | Rs.108,54,02,044.28 @ (+) 3.39% | M/s CIPPL-VSEDPL(JV) |  | Lr.No.14777/HMDA/DEV/CE/Miyapur-Gandimaisamma/2023-24, Dt.14.03.2024 |  | HMDA/DEV/CE/03/2024-25 | 12.06.2024 |  | EOT-I upto 31.10.2025 |  | Work is in progress. | 43.14 | 34.85
| II | Mehdipatnam Sky walk | 2020-21 |  | Skywalk | Construction of Skywalk with O&M of 2 years at Raithu bazaar, Mehdipatnam Hyderabad. |  | Govt. | G.O.Ms.No.82 G.O.Rt.No.106 | 03.06.2020, 11.02.2021 |  |  | Rs. 46.00
| II | Construction of Sum cum pump house at Balamrai | 2024-25 |  | Sump cum pump House | Construction of Sump, Reconstruction of Meeting Hall with staff Quarter, Shifting of /Reinstallation of existing 40KW Solar Plant and Relocation of Transformers at Balamrai- Near Paradise of SCB on NH-44. | 2223/HMDA/DEV/Div-II/E.E/NH-44/Sump/SCB/2024 | MC | 2223/HMDA/DEV/Div-II/E.E/NH-44/Sump/SCB/2024 | 21.09.2024 02.02.2025(Revised) | Rs.8.42 Cr(Revised from Rs.3.30Cr) | Rs.8.42 | 8.42 |  | 5,87,35,653.00 | 06 months |  |  | 5,77,43,020.46 @ (-) 1.69% | M/s Mahima Infrastructures |  | 14935/HMDA/DEV/CE/RCC Sump/SCB/2024-25, Dt.10.03.2025 |  | HMDA/DEV/CE/43/2024-25 | 12.03.2025
| II | Construction of Sum cum pump house at Bowenpally | 2024-25 |  | Sump cum pump House | Construction of Sump cum Pump house including pumping equipment and accessories, Staff Room, Store Room, Wash Rooms, Compound walls, drilling of 6 1/2" Borewell and Relocation of Transformers at Bowenpally Junction. | 2223/HMDA/DEV/Div-II/E.E/NH-44/Sump/SCB/2024 | MC | 2223/HMDA/DEV/Div-II/E.E/NH-44/Sump/SCB/2024 |  | Rs.3.27 Cr(Revised from Rs.2.80Cr) | 3.27 | 3.27 |  | 2,32,35,635.00 | 06 months |  |  | 2,24,50,270.54 @ (-) 3.38% | M/s Geetha Engineering Constructions Pvt. Ltd. |  | 15078/HMDA/DEV/CE/910 Kl Sump/BowenpallyJn/2024-25, Dt.22.03.2025 |  | HMDA/DEV/CE/02/2025-26 | 23.04.2025
| II | Construction of Sum cum pump house at Balamrai | 2024-25 |  | Sump cum pump House | Construction of Semi Underground Sump of capacity 10,00,000 Gallons at Race course and other connected works affecting under ROW of 60m on NH-44. |  |  | 15081/HMDA/DEV/CE/Race Course/Pump house/2024-25 | 10.03.2025 |  |  | 21.13
| II | Construction of Sum cum pump house at Balamrai | 2024-25 |  | Sump cum pump House | Reconstruction of 5,00,000 Gallon sump and pump house at Trishul lines pump house affecting under RoW of 60m on SH-01. |  | MC | 2231/HMDA/DEV/Div-II/E.E/SH-01/NH-44/Sump/SCB/2024-25 | 10.03.2025 |  |  | 7.5
| II | Widening of road at Kompally Municipality | 2024-25 |  | Road | Widening and Strengthening of existing road from Kompally kaman to Dhoolapally road via Nuzuveedu seeds and Aditya Ph-II in Kompally Municipality. |  | MC | 14948//HMDA/DEV/CE/QC/2024-25 | 09.01.2025 |  |  | 2.5
| II | Development of Blue Cross Building | 2024-25 |  | Building work | Development of Blue Cross Building in an extent of 2.00 Acres in Sy.No.333/P and 348/P of Quthbullapur(V&M), Medchal-Malkajgiri(Dist.). |  | MC | 14989/HMDA/DEV/CE/Blue cross building/2024-25 | 21.11.2024 |  |  | 8
| II | Miyapur Sy.No.100 & 101 fencing | 2024-25 |  | Fencing | Providing Fencing to HMDA land in Sy.No.100 & 101 with an extent of Ac. 445-34 Gts at Miyapur(V), Serilingampally(M), Ranga Reddy Dist. |  | MC | 14871/HMDADEV/CE/MiypurFencing/2024-25. | 21.06.2024 |  |  | 3.4
| II | Miyapur Sy.No. 20 & 28 fencing | 2024-25 |  | Fencing | Providing Chain Link Mesh Fencing to HMDA land in Sy.No.20 & 28 with an extent of Ac. 105.00 Gts at Miyapur(V), Serilingampally(M), Ranga Reddy Dist. |  | MC | 2015/HMDA/DEV/Div-II/Miyapur/Fencing & Boundary Pillars/2024-25 | 10.07.2024 |  |  | 1.9
| II | Boduppal Fencing | 2024-25 |  | Fencing | Providing Chain Link Fencing to HMDA land of Ext. Ac. 342-39 Gts in Sy.No.63/2 to 63/25 at Boduppal(V), Medipally(M), Medchal-Malkajgiri(Dist.) | 631/HMDA/DEV/Div-II/Boduppal fencing/24-25 | MC | 631/HMDA/DEV/Div-II/Boduppal fencing/24-25 | 22/09/2024 |  | 3.95 Cr | 3.95 |  | 2,86,09,165.00 | 03 months |  |  | (-) 39.99% Rs.1,71,68,359.92 | M/s Sri Ragavendra Waddera |  | 14936/HMDA/DEV/CE/fencing/Boduppal/2024-25, Dt.24.01.2025 |  | HMDA/DEV/CE/37/2024-25 | 18.02.2025 |  |  |  | Work held up due to court case
| II | Providing Infrastructure facilities to the balance plots in Uppal Phase-III layou | 2024-25 |  | Layout | Providing Infrastructure facilities to the balance plots in Uppal Phase-III layout, Uppal Bhagayath(V), Uppal(M), Medchal-Malkajgiri(Dist.) |  | MC |  | 17.03.2025 |  | 1.35 | 1.35 |  | 96,23,231 | 02 Months |  |  | Rs.60,63,597.85 @ (-) 36.99% | M/s HN infrastructures |  | 15092/HMDA/DEV/SE-II/fUB/INfra/Balance plots/2024-25, Dt.11.04.2025. |  | HMDA/DEV/SE-II/02/2025-26 | 27.05.2025
1 | VII | Bachupally Layout | 2023-24 | 27.09.2024 | Layout | Providing Infrastructure facilities for development of Layout in Sy.No.39 & 40 at Bachupally (V), Bachupally (M) in Medchal-Malkajgiri District. | G.O.Ms. No. 160 of MAUD Dept. | Govt. | G.O.Ms. No. 160 of MAUD Dept. Dt. 14.08.2023 | Dt. 14.08.2023 | - | 9.75 | 14 | HMDA/DEV/CE/03/02/2024-25, Dt:24.06.2024 | 7.72 | 6 months | 29/06/2024 to 15/07/2024 |  | 7.22 Cr & (-)6.39% | M/s. VIJAYA SAI ENGINEERS AND DEVELOPERS PVT.LTD. |  |  | - | HMDA/DEV/CE/11/2024-25 Dt: 27-09-2024 | 27.09.2024 | - | 1st EOAT upto 30.06.2025 2nd EOAT is under process | - | Work in progress | - | -
2 | VII | Chitkul Sy. No. 472 Fencing | 2022-23 |  | Fencing | Providing Barbed Wire Fencing with MS Angles at Sy.No.472 Ext Ac 49.03 Gts at Chitkul (V), Patancheruvu (M), Sanga Reddy District | 7037/HMDA/Dev/Div VII/SRD Layouts/2022-23 | MC | 7037/HMDA/Dev/Div VII/SRD Layouts/2022-23 | 14.03.2023 | - | 0.69 | 0.69 |  | 0.5 | 3 months |  |  | 0.35 & (-) 30.71 | Upputuri Ramesh |  |  |  | HMDA/DEV/SE-II/06/2023-24, Dated:: 28.07.2023 | 28.07.2023 |  |  |  | Work in progress | 0.26 | 0.23
| III | Nizam College Boys Hostel | 2023-24 | 26.07.2023 | Building work | Construction of Boys Hostel Building (G + 4) and class rooms Building (G + 2) at Nizam college campus, Hyderabad |  | Govt | GO Rt No. 583 dt:27.08.2022 GO Rt no.278 dt:09.05.2023 18.75 cr | 16.05.2022 |  |  | 18.75 |  | 16.13 | 15 months |  |  | 13.07 | M/s Sree Shivaram & Company |  |  |  | HMDA/SEV/CE/11/2023-24 | 26.07.2023 | Div-I 10.10% Excess |  |  | 75% completed |  | 7.13
| III | HMDA Grounds | 2025-26 | LOA dt:05.06.2025 | Others | Construction of Rain Water Collection Sump, injection borewell for ground water recharge , Laying of 900 mm and 600 mm dia R.C.C. NP-4 storm water pipe line, Laying of precast concrete blocks,Construction of compound wall with See through railing and Gates at HMDA Grounds, NTR marg | 15095/HMDA/DEV/CE/HMDA Grounds/NTR Marg/2025-26 | MC | 7.2 |  |  |  | 7.2
| III | P-2 & P-3 OU quarters | 2024-25 | 30.04.2025 | Heritage | Renovation of Professors quarters P-2 & P-3 at Osmania University (DTJ) Campus for setting up of museums and ethnic research centre by Adidhwani Foundation. | 15034/HMDA/DEV/CE/Prof.Quarters/OU/2024-25 | MC | 2.9 | 16.01.2025 |  |  | 2.9 |  | 2.29 | 6 months |  |  | 2.24 | M/s Varun Sai Constructions |  |  |  | HMDA/DEV/CE/08/2025-26 | 30.04.2025 |  |  |  | work halted due to local public protest
| III | Peddakanjarla Layout | 2024-25 | 28.09.2024 | layout | Providing Barbed Wire Fencing with MS Angles for the site at Sy.No. 125/2, 121/2 &120/2 to an extent of Ac 213.05 gts at Pedda kanjarla (V), Patancheruvu (M), Sanga Reddy District | 14808/HMDA/DEV/CE/Peddakanjarla/2023-24 | MC | 3.4 |  |  |  | 3.4 |  | 2.68 | 3 months |  |  | 1.77 | M/s M B Constructions |  |  |  | HMDA/DEV/CE/13/2024-25 | 28.09.2024 | Dev-I 7.08% Excess | EOT-III 27.09.2025 |  | work halted due to court stay order |  | 0.6
| III | Kodangal Municipalities | 2025-26 |  | others | Development of Junction and Median in Kodangal and Kosgi Municipalities | 15038/HMDA/DEV/CE/Kodangal & Kosgi/2024-25 | MC |  | 02.01.2025
| III | Musical Floating Fountain | 2022-23 |  | O&M | Supply, Installation, testing and commissioning of Musical Floating Fountains with the size 180m x 10m dia at Hussain Sagar Lake, Hyderabad with an O&M period of 3 years |  | MC | G.O.Rt.No.88 dt:24.02.2023 20.48 cr | 01.11.2022 |  |  | 20.48 |  | 17.02 | 42 months |  |  | 16.98 | M/s Meena Bazar Extension in JV with M/s Changsha Himalaya Musical Fountain Equipment, Co.Ltd. |  |  |  | HMDA/DEV/CE/44/2022-23 | 18.01.2023 |  |  |  | O & M in progress |  | 14.67
| III | Machinery O&M |  |  | O&M | Comprehensive Operation and Maintenance of Amphibious long boom excavator, dredge utility craft (DUC) Barge mounted Aerator and floating trash collectors (FTCS-5 big & 2 small) for 2years |  | MC |  |  |  |  | 9.6 |  | 9.5 | 24 months |  |  | 8.99 | M/s Bluedrop Enviro Pvt Ltd |  |  |  | HMDA/DEV/CE/39/2023-24 | 12.03.2024 |  |  |  | O & M in progress |  | 5.25
| III | Sector-II engaging labour |  |  | O&M | Engaging unskilled labour & tractors for removing and transportation of solid waste along shore area & water body from Jalvihar to Bathukamma Ghat (Sector- II) at Hussain Sagar Lake for 3 years |  | MC |  |  |  |  | 3.7 |  | 3.62 | 36 months |  |  | 3.48 | M/s Krishna Construction |  |  |  | HMDA/DEV/CE/50/2022-23 | 27.01.2023 |  |  |  | Maintenance in progress |  | 2.62
| III | Sector-I engaging labour |  |  | O&M | Engaging unskilled labour & tractors for removing and transportation of solid waste along shore area & water body from Tankbund to Jalvihar (Sector- I) at Hussain Sagar Lake for 3 years |  | MC |  |  |  |  | 3.1 |  | 3.02 | 36 months |  |  | 2.87 | M/s M. Prabhakar Reddy |  |  |  | HMDA/DEV/CE/52/2022-23 | 01.02.2023 |  |  |  | Maintenance in progress |  | 2.38
| III | STPs & I&Ds O&M |  |  | O&M | Operational and maintenance of 3 No.s STPs (along with attached I&Ds) and 7 Nos I&Ds around the Hussain Sagar Lake for 14 Months. |  | MC |  | 09.02.2024 |  |  | 9.7 |  | 7.19 | 14 months |  |  | 7.01 | M/s Aquatech Systems Asia Pvt.Ltd. |  |  |  | HMDA/DEV/CE/05/2024-25 | 28.06.2024 |  |  |  | Maintenance in progress |  | 5.87
| III | Automated Trash Collection System |  |  | O&M | Supply, Installation, commissioning and testing of Automated Trash Collection System at 4 different locations including Manning, Operation and Maintenance for 5 years around Hussain sagar Lake,Hyd |  | MC |  |  |  |  | 4.84 |  | 4.07 | 63 months |  |  | 4.07 | M/s Desmi India Private Limited |  |  |  | HMDA/DEV/CE/08/2021-22 | 27.10.2021 |  |  |  | Maintenance in progress |  | 3.68
| III | FTCs |  |  | O&M | Supply, delivery, assenbly, testing, commissioning of Additional floating trash collectors 2 Nos Big including 2 years comprehensive operation and maintenance | 14885/HMDA/DEV/CE/Addl.FTC/2024-25 | MC |  |  |  |  | 4.9 |  | 4.82 | 28 months |  |  | 4.77 | M/s Bluedrop Enviro Pvt Ltd |  |  |  | HMDA/DEV/CE/15/2024-25 | 15.10.2024 |  |  |  | Work in progress
| III | Bioremediation of HS Lake |  |  | O&M | Design, procure, implement proven technological intervention to arrest odour nuisance, algal bloom and to improve the water quality of Hussain sagar lake |  |  |  | 25.04.2025 |  |  | 2.31 |  | 2.31 | 12 months |  |  | 2.31 | M/s NACOF |  |  |  | HMDA/DEV/CE/04/2024-25 | 24.06.2024 |  |  |  | O & M in progress |  | 0.22
III
III
III
| IV | Budwel Layout |  |  | Layout Development | Development of Budwel Layout in Sy.No 283/P, 284/P, 287/P, 288/P, 289, 290, 291, 292,293, 294, 295, 296, 297, 298, 299/P of Budwel (V), Rajendra Nagar (M), R.R. District |  |  | G.O.Ms.No 209 | 04.10.2023 | NIL | Rs 525.00 Crores |  | 03.10.2023 | Rs.354.54 Crores | 18 months | [7 empty] | Rs. 36890.00 | Dt.12-06-2024 |  |  |  | 50% | 259.58 (Incl. Taxes) | 178.49 (Excl. Taxes)
|  | Widening and strengthening of existing road from Bachupally junction to Bowrampet and from Bahadurpally to kompally road from 0/0 to 7/0 in Quthbullapur Mandal and construction of 4 lane flyover at bachupally junction |  |  | Development | Widening and strengthening of existing road from Bachupally junction to Bowrampet and from Bahadurpally to kompally road from 0/0 to 7/0 in Quthbullapur Mandal and construction of 4 lane flyover at bachupally junction |  |  | G.O.Ms.No.207 Ratification Amount G.O.Ms.No.41 | 04.12.2021 30-03-2022 24.02.2022 | NIL | Rs 205.22 Crores |  | 16.04.2022 | Rs.180.22 Crores | 24 months | [7 empty] | Rs. 14691.42 | Date:23-09-2022 |  | 31.05.2025 |  | 83% | 12182.00 (Incl. Taxes) | 9638.00 (Excl. Taxes)
|  | Development of BT Road from Peeerzadiguda Kaman(NH-163) to Prathapa Singaram of PHC Limits |  |  | Development | Development of BT Road from Peeerzadiguda Kaman(NH-163) to Prathapa Singaram of PHC Limits |  |  | G.O.Ms.No.160 | 10.03.2022 | NIL | Rs 25.32 Crores |  | 30.03.2022 | Rs17.52 Crores | 09 months | [7 empty] | Rs. 1752.82 | Date:14-09-2022 |  |  |  | 95% | 1332.38 (Incl. Taxes) 1063.99 (Excl. Taxes) | 1063.99 (Excl. Taxes)
|  | Providing External Water proof Paint and Elevation with Structural Glazing & Mural Painting and Cement concrete Flooring and internal painting in Basement-2 and Fire Extinguishers and Sump to Multipurpose Building |  |  | Painting and Flooring | Providing External Water proof Paint and Elevation with Structural Glazing & Mural Painting and Cement concrete Flooring and internal painting in Basement-2 and Fire Extinguishers and Sump to Multipurpose Building | 15041/HMDA/DEV/CE/IAS/25-26 |  |  | 15.05.2024 | NIL | Rs.43,50,000/-Including GST |  | . TS No. HMDA/DEV/EE Div- IV/ 01 /25-26 | Rs.31,95,703.00/-(excluding GST) | 02 months | [7 empty] | Rs. 31, 95,703.00 | Dated 05–06–2025 |  |  |  | Commenced | NIL | NIL
|  | Extension of HMDA 100 feet road from Epistemo school circle to Ramky Orbit gate via Rock Garden park at Nallagandla Huda layout, R.R Dist |  |  | Road | Extension of HMDA 100 feet road from Epistemo school circle to Ramky Orbit gate via Rock Garden park at Nallagandla Huda layout, R.R Dist | 15104/HMDA/DEV/CE/Extn 100ft Rd/Nallagld Huda Layout/2025-26 |  |  | 27.03.2025 | NIL |  |  | 16.04.2025 | Rs. 6,22,62,874.00/- | [8 empty] | LOA issued Agreement to be concluded |  |  |  |  | Commenced | NIL | NIL
|  | Protection of Prime lands through Chain link fencing in the land to the Ext. Ac 99-14 Gts in Sy. No. 180 at Yenkepally(V), Moinabad(M), R.R Dist |  |  | Fencing | Protection of Prime lands through Chain link fencing in the land to the Ext. Ac 99-14 Gts in Sy. No. 180 at Yenkepally(V), Moinabad(M), R.R Dist | 14914/HMDA/DEV/SE-I/Yenkepally/2024-25 |  |  | 31.08.2024 | NIL | Rs. 1.62Crores |  | 03.09.2024 | Rs. 1.62 Crores | 03 months | [7 empty] | RS 74,26,561.86 | Dt 25.10.2024 |  |  |  | Commenced | NIL | NIL